November 25, 2009

Dear Jeff Hollett,

RE.: Funds for MSVU’s New Community Garden

It is with great excitement we submit this proposal concerning the Mount’s new community garden. A community garden is a plot of land where community residents grow food together, in shared or individual plots. It provides fresh produce, and opportunities for recreation, socializing and community building. A community garden increases food security, promotes environmental stewardship and encourages active living. Community gardening is also an opportunity to share skills and learn from one another. Our new garden provides MSVU with a unique opportunity to further increase hands-on learning opportunities and increase its presence as a leader in the community by becoming a role model of community gardening and modeling a healthy, active and socially conscious lifestyle on campus.

BACKGROUND

During the 2008-09 academic year, Sarah Wilson, a student in the Department of Applied Human Nutrition, conducted her Honours Thesis on the feasibility of implementing a community garden on the Mount campus. Results of her work:

- established the raised beds by the Meadows as a location for the community garden to transpire, with the Grounds Department willing to donate this land;

- identified that Applied Human Nutrition faculty would be interested in using a community garden as a teaching tool by incorporating “field trips” to the garden or having a garden expert guest speak during lectures and labs to reinforce course curriculum;

- confirmed that a dedicated Community Garden Coordinator would be necessary to ensure sustainability of the campus garden.

As a result of Sarah’s work, during the 2009-10 academic year StudentWorks is funding the Mount’s first ever student Community Garden Coordinator, Tanya James. There will be four main areas the Coordinator will focus on during this academic year: Networking, Planning, Promotion and Gardening.  While both Grounds Department and the Department of Applied Human Nutrition have agreed to contribute funds and resources to support the role of the Garden Coordinator, we are also seeking support from the Office of Student Experience. This additional support will better enable successful planning, promotion and indoor container gardening to occur during the academic year.

YEAR ONE GOALS

This proposal reflects both short term and long term goals for the Mount Garden. Short terms goals involve raising the garden’s profile on campus and in the community, connecting with MSVU departments and community groups interested in using the garden, and physical preparation of the garden for spring 2010. Specifically, the Garden Coordinator will work to:

- increase the profile of the garden on and off campus;

- raise awareness of the garden through posters, society and campus (electronic & hard) newsletters, MSVU newspaper The Sentinel, indoor gardens of potted herbs and vegetables, and special events;

- prepare the garden for the coming growing season: weeding, fall and spring crop planting, mulching and establishing an onsite compost pile;

- contact both academic and other departments, community organizations and local institutions to research interest levels, and create interest in working with the garden and making curriculum or program links.

LONG TERM GOALS

Long term goals of the Mount garden are to increase food security for nutritionally at-risk students on campus, to incorporate the garden into university curriculum for demonstration and educational purposes and peer to peer skill sharing. Many long term goals concord with MSVU’s strategic plan for implementing the university’s vision, as outlined in Destination 2012, such as community building, diversifying learning methods, increasing recreation opportunities on campus and increasing student/faculty input in campus programming. In addition, the garden will be a valuable tool for concretely demonstrating MSVU’s leadership on environmental sustainability, social justice, health promotion and creative educational techniques. Specific long term goals focus on Education, Food Security, Community Building, and Recreation.

Education

- The garden may be used as a teaching tool by interested academic departments; thus delivering university curriculum using diversified educational approaches. As all academic and administrative departments will have access to garden plots, interdisciplinary interaction will also increase (Destination 2012, Goal 3).

- A community garden will aid in creating a unique campus culture. The garden will broaden the variety of activities on campus educationally and recreationally. Goal 3 of Destination 2012 is to “create more opportunities for students, faculty and staff to participate in the intellectual, social, cultural and recreational life of the University”. The garden can be a medium for peer to peer learning and co-curricular activities.

- The garden will provide opportunities for hands-on workshops, skill sharing between participants, and learning from individuals who work both inside and outside of academia. It offers a more kinaesthetic and participatory learning experience than what is provided by classroom lectures. The garden fits into the university’s strategy to “Promote flexible learning approaches” to make MSVU programs more accessible (Destination 2012, Goal 4).

- A community garden dedicated to creating a local, organic example of food production provides the perfect backdrop to raise questions about the social, physical and environmental impacts of the current food system and raise awareness of alternatives. The topic of alternative food systems is ripe for debate; relevant to nutrition, biology, family studies, philosophy, women’s studies, sociology and anthropology, among other disciplines.

- Service Learning is an educational approach becoming better recognized by post secondary institutions in Canada. Students take theoretical skills learned in the classroom and, working with community organizations, create programs or provide services that meets their academic needs while also meeting the needs of the community.  Service Learning provides an opportunity for students to critically reflect on their values, their sense of social responsibility, and their leadership skills.  With food being a universal need and right, its relevance to any community is readily apparent, and educators, students and community members will find many common interests and opportunities for service.

Food Security

- The community garden can provide food for the Student’s Union Food Resource Centre, increasing student access to fresh produce and increasing income-related food security.

- Community food security and food resilience will also be impacted by the presence of a campus garden. The garden, with its emphasis on teaching and hands-on learning, will empower Mount community members by giving them the knowledge and skills to sustainably grow food in their own backyards, on window sills and decks.

Community Building

- Destination 2012 hopes MSVU will “encourage interaction with and service to the external community”, in part by developing outreach programs and service learning opportunities. The garden can help fulfil this mandate by offering programming to the off-campus community and providing volunteer opportunities to MSVU students and faculty to connect with community groups and organizations.

- The garden will also cultivate engagement in democratic culture by establishing a participatory approach to the planning and execution of the garden and garden related programs. Although research has shown that a dedicated Garden Coordinator is necessary for a sustainable program, the Coordinator will develop workshops, events, and facilitate planting and harvesting based on the needs of the Mount Community.

Recreation

- The garden will increase the quantity and diversity of recreational activities offered by MSVU. One strategy to implement Engagement, Goal 3 of Destination 2012 is to “improve physical facilities for recreation activities”. Gardening is a way of getting outside and being physically active while learning valuable skills that participants can use in their personal lives.

BUDGET

Although many outdoor materials are being donated by the Grounds Department, and the Applied Human Nutrition Department is providing support via Garden Coordinator supervision and absorbing promotional costs (printing, photocopying, etc.) the garden requires materials for the indoor sites such as pots, seeds and potting soil. In the 2010 growing season the main garden site will require seeds, seedlings and honorariums for guest speakers and workshop facilitators. Garden funding is as essential to the health of the community garden as good quality soil is to the health of plants. The garden needs “seed money” (both literally and figuratively) so that it can grow into something really special in future years. Getting the necessary supplies for the garden in its first year will not just support the garden in 2009-10, but will give a solid foundation for many planting seasons and harvests to come. Support from the Office of Student Experience will allow the MSVU Community Garden to blossom.

| Item | Description | Cost |
| --- | --- | --- |
| Garden Tools | Spades, shovels, soil, gloves, composter | Provided in-kind by Grounds Department |
| Water Supply and hose |  | Provided in-kind by Grounds Department |
| Office and advertising material | Printing and photocopying costs | Provided in-kind by the Nutrition Department |
| Indoor potting soil |  | $25 |
| Containers for indoor plants |  | $30 |
| Guest speaker honorariums | Estimating four guest speaker presentations | $25 x 4 = $100 |
| Repairs to the current raised beds | Repairs to be done on an “as needed” basis, requiring wood and nails | $50 |
| Seeds and seedlings |  | $65 |
| Organic fertilizers | e.g. Bone meal, manure | $25 |
| Total |  | $295 |

In conclusion, strategic reserve funding should be used to support the MSVU community garden because of the multitude of benefits afforded by a campus community garden and its ideal fit with the evolving MSVU culture as outlined in our Strategic Plan, Destination 2012. Community gardening addresses many critical and timely issues such as environmental degradation, lack of physical activity and the rise in chronic disease, Canadians’ disconnect with the industrial food system, and income-related food insecurity. The garden offers unique benefits to both on and off-campus communities, especially by offering interaction between members of each community. The MSVU community will benefit through service based learning opportunities, more tactile approaches to learning, increased student and faculty involvement in cultural and recreational life, and making interdisciplinary connections. The off-campus community will benefit from workshops and skill sharing. Both will benefit from increased food security, recreation, democratic engagement and networking within these groups.

Thank you for your consideration.

Submitted respectfully,

Tanya James (Garden Coordinator)

garden@msvu.ca

Rebecca Green-LaPierre (Supervisor)

rebecca.green@msvu.ca

457-6465